## Design Decisions
ID | Category | Decision | Rationale | Phase | Implementation Evidence | Verification | Status
ADR-01 | Architecture | Two-layer architecture | Headless training needs renderer-free sim | 1-6 | src/engine/ 9 files 0 renderer imports; src/renderer/ read-only | Import analysis Doc1 S3; arch-strategist verified | VERIFIED
ADR-02 | Architecture | Deterministic custom physics | Same inputs = same outputs | 1 | CarPhysics.ts bicycle model Pacejka. No Math.random() | 100 runs x 10K ticks = identical hash | VERIFIED
ADR-03 | Architecture | TypeScript + PixiJS | Type safety + WebGL 2D + Browser/Node | 1-6 | tsconfig strict:true. pixi.js in deps. Serena configured | tsc --noEmit = 0 errors. 366+ tests pass | VERIFIED
ADR-04 | Architecture | GSD single orchestrator | One brain not three | 1-6 | Conflicting commands excluded. All code via GSD | 6/6 phases 100%. 80+ atomic commits | VERIFIED
ADR-05 | Architecture | Six-phase build sequence | Each phase depends on previous | 1-6 | P1->P2->P3->P4->P5->P6 sequential dependency | All 6 phases complete in order | VERIFIED
ADR-06 | Architecture | Opus for architecture | Highest reasoning for spec/planning | 1-6 | Opus for planning. Sonnet for coding subagents | Quality visible in spec depth | VERIFIED
DD-07 | Car Physics | Simcade realism | Enough depth AI must learn | 1 | Weight transfer Pacejka grip limits | 60K steps to learn. Human feel validated | VERIFIED
DD-08 | Car Physics | Analog inputs | NNs output continuous; binary feels bad | 1 | InputProcessor keyboard smoothing. Gamepad P2. Box(3) | Xbox works. AI 3 continuous actions | VERIFIED
DD-09 | Car Physics | No dedicated drift | Natural oversteer only. Clean AI target | 1 | Pacejka oversteer. No drift state machine | Natural sliding. AI never optimizes drift | VERIFIED
DD-10 | Car Physics | 60Hz fixed tick decoupled | Headless skips draw | 1 | SimEngine fixed dt. GameLoop interpolates | Headless 13K+ tps. Browser 60fps | VERIFIED
DD-11 | Track Design | Spline centerline with width | Gold standard 2D racing + RL | 1 | TrackGeometry Catmull-Rom arc-length | 3 tracks. centerline in AI obs | VERIFIED
DD-12 | Track Design | Closed loops only | Simplifies laps checkpoints AI | 1 | All 3 closed. No p2p code | Lap counting works. P2P in v03 | VERIFIED
DD-13 | Track Design | 1 track P1-2 then 3-5 P3 | Don't over-commit early | 1,3 | Track 1 P1. Tracks 2+3 P3 | Track select 3 tracks thumbnails | VERIFIED
DD-14 | Track Design | Checkpoint gates ordered | Normalized progress for AI | 1 | CheckpointSystem ordered gates timing | reward.ts checkpoint primary signal | VERIFIED
DD-15 | Collision | Slide walls proportional penalty | Gradient for AI. No stop/bounce | 1 | CollisionSystem slide+penalty+nose rotation | AI 0 walls converge. Human: punish not stop | VERIFIED
DD-16 | Collision | Three-layer road/runoff/wall | Three tiers of consequence | 1,3 | SurfaceSystem friction both sides all tracks | AI off-track lighter than wall | VERIFIED
DD-17 | Collision | Ghost cars no collision | Pure time trial. No multi-agent | 6 | AI+human no collision. Ghost render | Cars pass through. Multi-agent v03 | VERIFIED
DD-18 | AI Design | 9 rays 180deg 22.5deg | Proven RL sweet spot | 4 | raycaster.ts 9 rays pre-computed | Obs confirmed. Training succeeds | VERIFIED
DD-19 | AI Design | 14-value observation | 9 rays + 5 state values | 4 | observations.ts 14 vals. per-component bounds | env_checker passes. SB3 trains Box(14) | VERIFIED
DD-20 | AI Design | Mildly privileged info | Compensates human spatial intuition | 4 | observations includes progress + centerline | Training validates they help | VERIFIED
DD-21 | Reward | Checkpoint progress + speed no centerline | Centerline fights racing lines | 4 | reward.ts no centerline. Default weights worked | AI uses full width. No tuning needed | VERIFIED
DD-22 | Reward | Four-tier penalties < progress | Harsh = timid AI | 4 | stillness/wall/offtrack/backward all < progress | Not timid. 0 wall contact converge | VERIFIED
DD-23 | Reward | Dense every tick + milestones | Non-negotiable continuous RL | 4 | Per-tick + checkpoint bonus. Sparse bug caught | <60K steps converge. Textbook ramp | VERIFIED
DD-24 | Game Features | Clean HUD timer laps speed minimap | No damage v02 | 2,3 | HudRenderer corners-only panels all elements | All functional in browser | VERIFIED
DD-25 | Game Features | No difficulty settings | Track + AI = difficulty | 3 | No difficulty menu. Volume+laps only | Damage model in v03 | VERIFIED
DD-26 | Game Features | Medium polish skid dust sparks sound | Real game not swallow P3 | 3 | ParticleSystem + SoundManager 100% synth | All visible/audible | VERIFIED
DD-27 | AI vs Human | ONNX browser inference | Fully static zero server | 6 | browser-ai-runner 23.7KB+816B | Runs browser 60fps | VERIFIED
DD-28 | AI vs Human | Simultaneous ghost racing | Competitive feeling | 6 | GameLoop dual-world cyan ghost glow | Both cars. Grace works | VERIFIED
DD-29 | AI vs Human | Spectator/demo mode | Zero cost triple duty | 6 | Same path human hidden camera AI | Selectable track select | VERIFIED
DD-30 | AI vs Human | Mode select track screen | Two clicks to racing | 6 | ScreenManager mode buttons cards | Track->mode->race. Two clicks | VERIFIED
DD-31 | AI vs Human | Local leaderboard localStorage | Best lap human+AI | 6 | tdr-leaderboard-v1 BestTimes.ts | Persists across sessions | VERIFIED
DD-32 | AI vs Human | KILLED: Attract mode | Spectator covers it | N/A | AVH-04 killed. No code | Spectator=demo | VERIFIED
DD-33 | AI vs Human | DEFERRED: Ghost replay v03 | Live ONNX instead | N/A | No replay code. Live inference | In v03 parking lot | VERIFIED

## Phase Objectives
Phase | Objective | Key Deliverable | Success Metric | Actual Result | Tests | Status
1 | Core simulation engine | Deterministic tick-based physics | 10K+ tps deterministic | 13K+ tps 100 runs identical | 214 | VERIFIED
1 | Bicycle model | Weight transfer Pacejka oversteer | Simcade analog control | Full model smoothing gamepad | 214 | VERIFIED
1 | Collision system | Slide-along wall collision | No stop gradient | Slide penalty nose rotation | 214 | VERIFIED
1 | Track geometry | Catmull-Rom splines checkpoints | Closed loops ordered | Arc-length checkpoint sys | 214 | VERIFIED
2 | PixiJS renderer | WebGL reading engine state | Read-only no mutation | WorldRenderer read-only zero mutations | - | VERIFIED
2 | Playable game | Race in browser | Camera HUD timestep | Dynamic zoom corners HUD WASD gamepad | - | VERIFIED
3 | Multiple tracks | 3+ playable tracks | Variety for training+play | 3 tracks thumbnails best times | - | VERIFIED
3 | Sound system | Engine screech impact UI | Synthesized no assets | 100% Web Audio synthesis volume sliders | - | VERIFIED
3 | Visual effects | Skid marks particles flash | Medium polish | Skid dust sparks checkpoint flash | - | VERIFIED
3 | Menu system | Main->Track Select->Race | Animated settings | Full flow volume laps thumbnails | - | VERIFIED
3 | Race completion | Configurable laps finish overlay | Finished in engine | ARCH-01 fireworks fanfare breakdown | 315 | VERIFIED
4 | AI observation | 9-ray raycaster 14-value | Spatial+state | Pre-computed per-component bounds | 48 | VERIFIED
4 | Reward function | Dense per-tick milestones | Progress speed penalties | Sparse bug caught pre-execution | 48 | VERIFIED
4 | Bridge infra | WebSocket Node<->Python | <1ms 0 crashes | 0.251ms 106K steps 0 crashes | 65 | VERIFIED
4 | Gymnasium client | Python env_checker | SB3-ready | check_env passes clean | 68 | VERIFIED
5 | Training infra | SB3 PyTorch TensorBoard | Metrics correct | Callback lifecycle bugs caught | - | VERIFIED
5 | PPO training | Checkpoint resume evaluate | Full lifecycle | Track 1 clean laps <60K steps | 12 Py | VERIFIED
5 | Production model | Track 3 2M steps | 0 wall contact | 2M 2hrs 0 walls variance 0.994 | - | VERIFIED
6 | ONNX export | model.onnx stats.json | <50KB browser | 23.7KB 816B bug fixed | - | VERIFIED
6 | vs AI mode | Ghost racing grace period | Both cars 5s grace | Dual-world cyan glow DNF | 366+ | VERIFIED
6 | Spectator | AI drives solo | Camera follows AI | Human hidden camera follows | 366+ | VERIFIED
6 | Mode+leaderboard | Buttons localStorage | Two clicks persist | Track cards mode buttons | 366+ | VERIFIED

## GSD Interview
GSD Question | Decision | Rationale | How Verified | Status
Where does it run? | Browser + headless Node | Browser humans headless AI | pnpm dev + run-bridge 3980 sps | VERIFIED
Driving feel? | Simcade | Physical not punishing | Human P2. AI 60K not trivial | VERIFIED
Done looks like? | Full demo mode | URL watch AI try beat it | Solo+vsAI+Spectator. ONNX static | VERIFIED
Thoroughness? | Standard 5-8 phases | 6 phases 3-5 plans each | 6 phases plans in range | VERIFIED
Parallel? | Yes | Waves for independent tasks | Wave execution all phases | VERIFIED
Research first? | Yes | Catches domain gotchas | Research P1-4 skip P5 redundant | VERIFIED
Verify plans? | Yes | Gaps before tokens | 15/15 deepen caught real bugs | VERIFIED
AI models? | Quality Opus | Opus reasoning for specs | Opus planning Sonnet coding | VERIFIED

## Defect Prevention
# | Phase/Plan | Bug Caught | Severity | What Would Have Shipped | Fix Applied | Caught By | Status
1 | P2-P3 | Game state machine in renderer ARCH-01 | CRITICAL | AI bridge imports renderer breaks headless | RaceController extracted to engine | arch-strategist | FIXED
2 | P3 | Finish-detection in renderer | HIGH | Race completion duplicated state | Finished phase in engine RaceController | /deepen-plan | FIXED
3 | P3 | Two-formatTime merge trap | MEDIUM | Duplicate utils inconsistent display | formatRaceTime+formatBestTime to utils | /deepen-plan | FIXED
4 | P4-01 | Sparse reward not dense | CRITICAL | Training completely fails no signal | Per-tick signal + checkpoint bonus | /deepen-plan | FIXED
5 | P4-01 | Speed bonus 37x too high | CRITICAL | AI spins circles never races | speedBonus to 0.0 progress dominates | /deepen-plan | FIXED
6 | P4-01 | Wall detect false after resolution | HIGH | Zero wall penalty walls=guardrails | Padded-radius before AND after | /deepen-plan | FIXED
7 | P4-02 | offtrackPenalty casing mismatch | HIGH | Off-track silently ignored | Casing standardized TS strict catches | /deepen-plan | FIXED
8 | P4-02 | 3x redundant distanceToTrackCenter | MEDIUM | 3x perf hit observation compute | Compute-once single call shared | /deepen-plan | FIXED
9 | P5-01 | record vs record_mean corruption | HIGH | TensorBoard metrics silently wrong | record_mean per-step record rollout-end | /deepen-plan | FIXED
10 | P5-01 | Cumulative not per-lap time | MEDIUM | Lap times as cumulative totals | Per-lap delta from previous end | /deepen-plan | FIXED
11 | P6-00 | pickle.load security CWE-502 | HIGH | Arbitrary code execution | SB3 safe loading API | /deepen-plan | FIXED
12 | P6-01 | VecNormStats case mismatch NaN | CRITICAL | All inference NaN AI does nothing | camelCase TS snake_case Py export converts | /deepen-plan | FIXED
13 | P6-02 | AI heading 90deg wrong | HIGH | Ghost drives sideways demo broken | Heading offset corrected AiCarRenderer | /deepen-plan | FIXED
14 | P6-02 | WASM tensors undisposed 43KB/min | MEDIUM | Memory leak tab crash ~45min | Tensors disposed after inference | /deepen-plan | FIXED
15 | P6-03 | AI stepping during countdown | HIGH | AI 3-second head start every race | Stepping gated on racing phase | /deepen-plan | FIXED

## Summary
Requirements Traceability Matrix - Summary
Top-Down Racer v02 - Evidence Package Doc 2
March 2026
TRACEABILITY COVERAGE
Design decisions traced | 33 / 33 | 100% coverage
Phase objectives traced | 22 / 22 | 100% coverage
GSD interview decisions | 8 / 8 | 100% coverage
Pre-execution defects | 15 / 15 | 100% catch rate
BUILD METRICS
Phases completed | 6 / 6 | 100%
Git commits | 80+ | Atomic per task
Automated tests | 366+ | TS + Python
Hand-written code | 0 lines | 100% autonomous
DEFECT BREAKDOWN
CRITICAL pre-execution | 4 | Sparse reward, speed 37x, VecNorm NaN, ARCH-01
HIGH pre-execution | 6 | Wall detect, casing, heading, countdown, pickle, metrics
MEDIUM pre-execution | 5 | Performance, timing, merge, leak, formatTime
KEY PERFORMANCE
Headless speed | 13,000+ tps | Target 10,000
AI to competent | < 3 min | 60K steps Track 1
ONNX model | 23.7 KB | Browser zero server
Determinism | 100% | 100 runs x 10K = identical